## Sheet1
Bug Reporting
Test case-001
Issue: | Verification code unable to sent
Reproducing steps
1. Go to URL: |  | https://www.mobileaction.co/app/android/us/ekhanei-com/com.ekhanei.app
2. goto to the site
3. tap on Sign up with LinkedIn up for free button
4. Tap on signup with linkdin button
Env: | Production
Module: | Sign Up
Severity: P1
Responsible QA: |  | Arpita Paul
Test case-002
Issue: | First name , last name and Company name has password option
Reproducing steps
1. Go to URL: |  | https://www.mobileaction.co/app/android/us/ekhanei-com/com.ekhanei.app
2. tap on Sign up for free button
3. Tap on signup with linkdin button
4. Then go to second step
Env: | Production
Module: | Sign Up
Severity: P1
Responsible QA: |  | Arpita Paul
Test case-003
Issue: | invalid phone nubmer is accepted here
Reproducing steps
1. Go to URL: |  | https://www.mobileaction.co/app/android/us/ekhanei-com/com.ekhanei.app
2. tap on Sign up for free button
3. Tap on signup with linkdin button
4. Then go to second step | Production
Env: | Production
Module: | Sign Up
Severity: P1
Responsible QA: |  | Arpita Paul
Test case-004
Issue: | When someone has not had a LinkedIn account but he wants to create a new account by clicking on the join now button but the button is not working.
Reproducing steps
1. Go to URL: |  | https://www.mobileaction.co/app/android/us/ekhanei-com/com.ekhanei.app
2. Click on "Sign In" button. 3. A new page will appear having Sign In and Sign Up button. Click on "Sign Up" button 4. Put test data on Name field 5. Click Create account button
Env: | Production
Module: | Sign Up
Severity: P1
Responsible QA: |  | Arpita Paul
Test case-005
Issue: | Invalid email address accepted
Reproducing steps
1. Go to URL:
2. tap on the Sign up for free button 3. fill email option 5. Click Create account button |  | https://www.mobileaction.co/app/android/us/ekhanei-com/com.ekhanei.app
Env: | Production
Module: | Sign Up
Severity: P1
Responsible QA: |  | Arpita Paul